ECM3401 Project Logbook

Student Name: Maxime Pierre Claude Reynaud

Project Name: Buffer Overflow Attacks in the Era of Gen-AI

Internal Supervisor: Anne Kayem

External Supervisor: N/A

Log of Activities

| Date | Key activities | Outcomes | Comments/Action plans |
| --- | --- | --- | --- |
| 09/26/2025 | First Metting with supervisor | Better understanding of the workflow, major questions answered | Start reviewing literature, get familiarized with Latex template |
| 09/30/2025 | Started Reviewing Literature and planning review | More understanding of the direction I want my review to take and what I want to demonstrate | I need to first define exactly what is a Buffer overflow and how it works and do the same for Gen-AI. The structure of my review should follow methodical introduction, main body and then conclusion plan with sections structured by research topics. |
| 10/03/2025 | Second Meeting with supervisor | Close monitoring of progress leading to constant implication on the project, better targeted literature review and early questions answered | Continue reviewing literature and get started on writing abstract, took contact with another student doing the same dissertation subject |
| 10/04/2025 10/05/2025 | Initial reading process to identify correct sources | Started reading Buffer overflows and Gen-AI related papers and articles to understand current situation on these topics | I need to continue this process until I have identified a possible gab in the papers and a possible structure for my review |
| 10/10/2025 | Third Meeting with supervisor | Making sure we identified correct and relevant sources to understand and illustrate the review, checkup on current progress | Verifying correctness and relevancy of resources identified, understanding how they can fit in my early plan |
| 10/13/2025 | Designing early plan for the literature review | With the identified resources and structure started my plan and made early draft of the project | Designing the plan with the relevant literature as illustration, continuing my reading |
| 10/17/2025 | Fourth Meeting with supervisor | Keeping up with the time constrain, making sure that I am going in the right direction for my study and my early plan is correct | Good overview of my peers progress and feedback of the early plan and resources |
| 10/18/2025 10/19/2025 10/20/2025 10/21/2025 10/22/2025 10/23/2025 | Finished plan and started first draft for the review | Finished early plan with relevant literature, defined concrete structurer and now started writing introduction and first parts | Initial writing work to put my ideas on paper, following the plan and using the relevant resources |
| 10/24/2025 | Fifth Meeting with supervisor | Keeping track of our progress, weekly checkup and advice on how to finalise plan and continue writing first draft | Good feedback on our current situation and activities, insight on the correctness of my plan of understanding of rod ahead |
| 10/26/2025 | Realising I was writing a dissertation not a literature review | While writing my first draft I realised I was not going in the right direction and corrected the structure | Rewrote most of the first draft with emphasis on comparing studies instead of analysing them |
| 10/28/2025 to 11/05/2025 | Wrote the complete first draft of the review | Completed full first draft covering all planned sections of the literature review, from buffer overflow taxonomy through to Gen-AI assisted vulnerability detection | The draft ended up being quite long and needed heavy editing, but getting everything down helped me see the gaps in my argument and where I was repeating myself |
| 11/07/2025 | Sixth Meeting with supervisor | Checkup on project plan, current draft and understanding feedback from supervisor on what we sent | Supervisor pointed out areas where my review was too descriptive and not critical enough, also suggested I tighten the scope before submitting |
| 11/10/2025 to 11/20/2025 | Revised and submitted literature review | Edited the draft based on supervisor feedback, cut down word count, added more critical analysis and comparison between studies | Felt much better about the final version, though the hardest part was cutting things I spent ages writing. Submitted on time which was a relief |
| 11/25/2025 | Seventh Meeting with supervisor | Discussed feedback on submitted review and started planning the dissertation proper, agreed on experimental approach | Supervisor happy with the review overall. We agreed the dissertation would focus on benchmarking Gen-AI models against static analysis tools for buffer overflow detection |
| 11/27/2025 to 11/30/2025 | Background research on Gen-AI model capabilities and access | Tested access for all 7 models, read system cards and documentation to understand each model’s architecture and reasoning features | Some models were harder to get running than others. Had to figure out how to enable thinking mode on DeepSeek and compare it with the non-thinking version |
| 12/01/2025 to 12/12/2025 | Designed experiment methodology and wrote vulnerable C programs | Created 5 buffer overflow scenarios in C covering stack, heap, integer overflow, format string, and a realistic CVE-based GIF parser vulnerability | Spent a lot of time making the vulnerabilities realistic but not trivial. The GIF parser one took the longest because I wanted it to feel like a real-world bug, not a textbook example and there is no POC |
| 12/13/2025 to 01/11/2026 | Christmas vacation | Did some light reading on prompt engineering techniques over the break, skimmed a few papers on how other studies structured their AI benchmarks | Mostly took the break off but kept a few articles on hand for when I felt like reading. Came back with a clearer idea of how to structure the prompts |
| 01/12/2026 to 01/19/2026 | Designed prompts and scoring rubric, tested C programs | Developed Prompt A (single-stage baseline) and Prompt B (4-stage pipeline), created weighted scoring formula, compiled and debugged all 5 C programs | Deciding on the weights for each scoring criterion was tricky. Also found a couple of bugs in my own C code which was ironic given the project topic |
| 01/20/2026 | Eighth Meeting with supervisor | Presented experiment design, scoring rubric and prompt strategies for approval before running tests | Got the green light to start testing. Supervisor suggested also running static analysis tools as a baseline which I had already planned, so that was reassuring |
| 01/21/2026 to 01/25/2026 | Pilot testing with 2 models to validate scoring rubric | Ran trial tests with GPT-5.2 and Claude Sonnet to check the scoring criteria worked in practice and could be applied consistently | Had to adjust some rubric wording after realising certain criteria were ambiguous when applied to real outputs. Better to catch this now than halfway through |
| 01/27/2026 | Ninth Meeting with supervisor | Quick check-in on pilot results, confirmed rubric adjustments were sensible before starting full Prompt A runs | Short meeting, mainly just a sanity check. Supervisor agreed with the changes I made to the scoring criteria |
| 01/28/2026 to 02/09/2026 | Ran Prompt A tests across all 7 models | Completed 70 test runs (2 per model per vulnerability) using the single-stage prompt, recorded all outputs and scored them | Some models were surprisingly inconsistent between runs on the same code. GPT-5.2 and Claude Opus were the most reliable. DeepSeek without thinking mode struggled quite a bit |
| 02/10/2026 | Tenth Meeting with supervisor | Reviewed Prompt A results, discussed emerging patterns and which models to take forward for Prompt B | Agreed to test top 3 models with the multi-stage pipeline since running all 7 again would take too long and the bottom performers were clearly not competitive |
| 02/11/2026 to 02/16/2026 | Organised data and ran static analysis baselines | Created CSV files with all scored results, calculated averages per model. Ran Semgrep (1/5 detected) and SonarQube (2/5 detected) as baselines | Seeing the numbers laid out made patterns much clearer. Was honestly surprised how limited the static tools were on my test cases |
| 02/17/2026 | Eleventh Meeting with supervisor | Presented static analysis comparison and Prompt A rankings, confirmed top 3 selection (GPT-5.2, Gemini 3, Claude Opus) for Prompt B | Supervisor found the static analysis comparison really compelling and said it would strengthen the argument for Gen-AI in the dissertation |
| 02/18/2026 to 02/28/2026 | Ran Prompt B (4-stage pipeline) on top 3 models | Completed 30 runs with the structured pipeline approach, scored all outputs. Results showed improvement for some models but not all | The pipeline approach helped Gemini 3 the most, it went from struggling with analysis to giving much more structured responses. Claude Opus was already strong so the improvement was smaller |
| 03/01/2026 to 03/02/2026 | Started designing and running evasion technique tests | Designed 3 evasion techniques (misleading comments with prompt injection, code obfuscation, decoy security code) and ran initial batch on first model | Spent most of the time designing the evasion scenarios rather than running them. Wanted each technique to test a genuinely different weakness |
| 03/03/2026 | Twelfth Meeting with supervisor | Quick mid-week update on evasion testing progress, shared early results showing some models were vulnerable to prompt injection | Supervisor was really interested in the prompt injection findings and encouraged me to dig deeper into why some models resisted it better |
| 03/04/2026 to 03/09/2026 | Completed evasion tests and analysed results | Finished all 63 evasion test runs across top 3 models, built scoring heatmaps and calculated resilience percentages | The prompt injection via misleading comments actually tricked some models which I did not expect. Heatmaps really helped visualise which models were more robust |
| 03/10/2026 | Thirteenth Meeting with supervisor | Presented all experimental data including evasion results, discussed how to structure the results and discussion chapters | Supervisor was impressed with the evasion testing angle and said it would make the dissertation stand out. Gave advice on presenting scoring tables clearly |
| 03/11/2026 to 03/16/2026 | Wrote methodology and results chapters | Drafted Sections 3 and 4 covering the full experiment design, all results tables, heatmaps, and Prompt A vs B comparison | Writing up results took longer than expected because I kept finding small things to double-check in my data |
| 03/17/2026 | Fourteenth Meeting with supervisor | Reviewed methodology and results draft, got feedback on table formatting and where the analysis needed more depth | Supervisor said the results were solid but wanted me to add more interpretation, not just present numbers but explain what they mean |
| 03/18/2026 to 03/23/2026 | Wrote discussion, introduction, and background sections | Drafted Section 5 (discussion linking results to objectives), Section 1 (introduction with aims/objectives), and Section 2 (technical background) | The discussion section was the hardest to write without being repetitive. Tried to keep intro and background under 2 pages as per the spec |
| 03/24/2026 | Fifteenth Meeting with supervisor (last before Easter) | Reviewed near-complete draft, got feedback on conclusion, abstract, and areas that needed tightening before the break | Main feedback was that my conclusion was too short and my abstract needed work. Also flagged a few typos. Agreed I would use Easter to revise and polish since deadline is right after |
| 03/25/2026 to 03/27/2026 | Started revisions based on supervisor feedback | Rewrote abstract, started expanding conclusion with contributions and future work sections | Wanted to get as much done as possible before the break officially started so I could focus on polishing during Easter rather than rewriting |
| 03/28/2026 to 04/05/2026 | intensive dissertation revision | Expanded conclusion to include broader implications and personal reflection, fixed score inconsistencies, rewrote Section 5.2 with per-objective analysis paragraphs | Normally I would take it easy during the break but the deadline is right after Easter so I had no choice. Spent most days working on this, felt like crunch time |
| 04/06/2026 to 04/12/2026 | proofreading and page limit compliance | Fixed all remaining typos, checked every reference, cut content to meet the 20-page body limit, peer reviewed with a classmate | Cutting down to 20 pages was painful since every section felt important. Getting a classmate to read it helped catch things I had become blind to |
| 04/13/2026 to 04/19/2026 | final formatting and deliverables | Finalised formatting, prepared AI usage log with prompt hyperlinks, completed this activity logbook, started working on presentation | Almost there. The AI usage log took longer than expected since I had to track down all the conversation links from months of testing |
| 04/21/2026 | Sixteenth Meeting with supervisor | Final check-in before submission and poster presentation, reviewed polished draft and all supporting documents | A few minor wording suggestions. Felt good to get the final approval |
| 04/22/2026 | Final submission preparation | Compiled all deliverables including dissertation, activity log, and presentation materials for submission | Ready to submit. Feeling good about the work overall even though there are always things I wish I could improve with more time |